Pre-Event Planning

Determine Date & Location

i.  Get the necessary permits from the city.

Map out exact race route.

Create volunteer committee

i.  Set committee meetings

ii.  Determine volunteers needed

Determine Registration Logistics

i.  How will people pre-register?

ii.  What information do we need to gather?

iii.  Signed Liability Waiver Approval

Determine Race day set-up.

i.  Determine timeline for Set-up

ii.  Where will people park?

iii.  Where should we place the registration table?

1.  Determine sign-in process and numbering.

2.  Hand out timing buttons.

iv.  Where should we place the medical tent?

v.  Where should we have water stops?

vi.  Where should we have the award ceremony?

1.  Obtain race medals

2.  Determine ceremony host.

3.  Determine A/V needs.

4.  Write ceremony script.

vii.  Determine where we need signage.

1.  Design Signage

2.  Print Signage

viii.  Set-up place and time for sponsors to drop of bag filling cache keys.

1.  Gather volunteers and have bag filling get together.

ix.  Find a volunteer photographer or videographer.

Marketing

Confirm Naming

Create & Approve Logo

Create the “why” story

i.  What challenges are faced that drive fundraising?

ii.  Contact people who have or will benefit from fundraising and tell their story.

Create Brochure & Registration Form for Runners/Walkers

i.  Distribute brochures to running stores or places of interest

Create Brochure & Registration Form for Sponsors

i.  Determine Sponsorship Levels & Incentives

Create Posters/Flyers for Distribution

Create Website

i.  Allow people to register online

Additional Marketing Online

i.  Create YouTube Video Channel

1.  Make video promoting event

2.  Shoot video at event to promote next year

3.  Gather stories of people who have benefited.

ii. Create a Flickr Account

1.  Post pictures online.

2.  Create social networking profiles

3.  Create Events

4.  Make Friends

Design & print volunteer & racer t-shirts. Add to racer bags.

Fundraising

Gather list of potential donors

i.  Send Brochure

ii.  Hand brochures to every foreseeable participant or sponsor

iii.  Make follow-up phone calls

Determine how money will be collected.

Race Day Operations

Set-up

i.  Registration

1.  Hand out numbers & timing censors & goodie bags

2.  Coat check, bag check?

ii.  Signage

iii.  Watering Stations

1.  Water must be pre-purchased

2.  Volunteers in place

iv.  A/V, Award Ceremony

1.  Electricity must be available, figure how much you need.

v.  Handout radios for on-site communication

vi.  Medical tent

1.  Find volunteer medical staff

2.  Gather ice & supplies

Run the Race

Post results for serious runners.

Tear down the event

Follow-up & Evaluation

Match goals with actual results

Follow-up communication with racers and volunteers

i.  Send out report on how money was used.

ii.  Promote next year’s race